{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["DevOps Bugs","Analysis"],"not_rendered":{"pivot_tables":7},"read":"whole","date_system":"1900"}

{"sheet":"DevOps Bugs","index":0,"n_rows":172,"n_cols":16,"rows_kept":172}
["ID","Area Path","Title","Assigned To","State","Sub state","Customer","Priority","Severity","Created Date","Tags","Work Item Type","Parent","Bug Type","Fault","Hotfix in Release"]
[517606,"Calidus\\CTL","CTY CTL - Call Logging - Booking - Vehicle Lookup shows no vehicles",null,"Closed",null,"CTY",2,"3 - Medium","2023-09-19T16:39:12","CTY-E2E","Bug",null,null,"Program error","CTL 3.01.08"]
[517612,"Calidus\\CTMS","CTY CTMS Can't enter default vehicle for a driver",null,"Closed",null,"CTY",2,"3 - Medium","2023-09-19T16:56:30","CTY-E2E","Bug",null,"Functional",null,"CTMS ER044-073"]
[517613,"Calidus\\CTL","CTY CTL Call Logging - have to click depot lookup button twice",null,"Closed",null,"CTY",2,"3 - Medium","2023-09-19T16:57:33","CTY-E2E","Bug",null,"Functional","Design error"]
[517615,"Calidus\\EPOD Device","CTY EPOD Device Vehicle Search shows vehicles already inspected in fleet inspection","Susan Rose <srose@aptean.com>","Closed","On Test","CTY",4,"4 - Low","2023-09-19T17:17:11","CTY-E2E","Bug",null,null,"Missing function"]
[517616,"Calidus\\EPOD Device","CTY EPOD Device - Inspecting vehicle with tyre details doesn't show the details.",null,"Closed",null,"CTY",1,"2 - High","2023-09-19T17:24:13","CTY-E2E","Bug",null,null,"Program error (rework)"]
[517620,"Calidus\\EPOD Device","CTY EPOD No inspection information on service report",null,"Closed",null,"CTY",2,"1 - Critical","2023-09-19T17:55:24","CTY-E2E","Bug",{"$nulls":3},"APK 4.05.00.85"]
[517623,"Calidus\\CTMS","CTY CTMS-PORTAL - No vehicle details shown on Portal for Fleet Inspection",null,"Closed",null,"CTY",2,"2 - High","2023-09-19T18:04:42","CTY-E2E","Bug",null,"Functional"]
[517624,"Calidus\\EPOD Admin","CTY EPOD - Can't see EPOD Service Report from Portal",null,"Closed",null,"CTY",2,"2 - High","2023-09-19T18:06:30","CTY-E2E","Bug"]
[517783,"Calidus\\CTMS","CTY CTMS Order Vehicles section not exported to Elucid.",null,"Closed",null,"CTY",2,"1 - Critical","2023-09-20T08:43:28","CTY-E2E","Bug",null,"Functional","Missing function","CTMS ER044-079"]
[517795,"Calidus\\CTMS","CTY CTMS Services supplied from Other Work and Vehicle lines have not been added to the order.",null,"Closed","Installed on UAT","CTY",2,"1 - Critical","2023-09-20T08:54:41","CTY-E2E","Bug",null,"Functional","Design constraint","CTMS ER044-076"]
[517813,"Calidus\\CTMS","CTY CTMS Services Supplied not populated on order items",null,"Closed",null,"CTY",2,"1 - Critical","2023-09-20T09:24:35","CTY-E2E","Bug",null,"Functional","Design error","CTMS ER044-080"]
[517894,"Calidus\\CTL","CTY CTL Call Logging - Nearest stock holding location is not showing",null,"Closed",null,"CTY",2,"3 - Medium","2023-09-20T11:46:33","CTY-E2E","Bug",null,"Functional","Design error","CTL 3.01.08"]
[517896,"Calidus\\CTL","CTY CTL Call Logging - Quantity should not be allowed to change on Fit New",null,"Closed",null,"CTY",2,"3 - Medium","2023-09-20T11:54:42","CTY-E2E","Bug",null,null,"Program error","CTL 3.01.08"]
[517899,"Calidus\\CTMS","CTY CTL Call Logging - No services displayed in Services Only table",null,"Closed",null,"CTY",2,"2 - High","2023-09-20T12:03:28","CTY-E2E","Bug",null,"Functional","Program error","CTMS ER044-077; CTL 3.01.08"]
[517902,"Calidus\\CTL","CTY CTL Call Logging - Driver defaulted vehicle even though there is no default.",null,"Closed",null,"CTY",2,"3 - Medium","2023-09-20T12:15:14","CTY-E2E","Bug"]
[517913,"Calidus\\CTMS","CTY CTMS ELUCID API INTERFACE - Not including TO_DELIVER quantities",null,"Closed","Installed on UAT","CTY",2,"1 - Critical","2023-09-20T12:39:42","CTY-E2E","Bug",null,"Functional","Missing function","CTMS ER044-076"]
[517921,"Calidus\\CTMS","CTY CTMS-EPOD INTERFACE - Removal tyres have description/price of installed product ","Dominic Murphy <dmurphy@aptean.com>","Closed","Installed on PRD","CTY",4,"4 - Low","2023-09-20T12:55:41","CTY-E2E","Bug",null,"Functional","Program error (rework)","CTMS ER045-004"]
[517981,"Calidus\\CTMS","CTY CTMS-EPOD Interface - Update from EPOD job failed with invalid package information","Paul Roscoe <proscoe@aptean.com>","Closed","On-hold","CTY",4,"4 - Low","2023-09-20T15:29:04","CTY-E2E","Bug",null,"Services Bug"]
[518002,"Calidus\\CTMS","CTY CTL Call Logging - Subsequent job booked onto already completed stop","Dominic Murphy <dmurphy@aptean.com>","Closed","On Test","CTY",4,"4 - Low","2023-09-20T16:10:32","CTY-E2E","Bug",null,"Services Bug",null,"CTMS ER044-090"]
[518003,"Calidus\\EPOD Device","CTY EPOD - Subsequent collection job on existing load not visible on device",null,"Closed",null,"CTY",3,"2 - High","2023-09-20T16:17:59","CTY-E2E","Bug",null,null,"Program error"]
[518014,"Calidus\\CTL","CTY CTL or CTMS-EPOD Interface - Inspection details not created",null,"Closed",null,"CTY",2,"2 - High","2023-09-20T16:48:39","CTY-E2E","Bug",null,null,"Unable to replicate"]
[518223,"Calidus\\CTL","CTY CTL Call Logging - Error when creating job",null,"Closed","Installed on UAT","CTY",2,"2 - High","2023-09-21T10:06:39","CTY-E2E","Bug",{"$nulls":3},"CTL 3.1.9, CTL3.1.11"]
[518228,"Calidus\\CTL","CTY CTL Call Logging - Duplicated tyre positions when adding tyre",null,"Closed",null,"CTY",2,"3 - Medium","2023-09-21T10:15:40","CTY-E2E","Bug",null,null,"Program error","CTL 3.01.08"]
[518256,"Calidus\\EPOD Admin","CTY EPOD Service report photos are misaligned","Dominic Murphy <dmurphy@aptean.com>","Closed","On Test","CTY",3,"4 - Low","2023-09-21T11:09:00","CTY-E2E","Bug"]
[518287,"Calidus\\CTMS","CTY CTL Call Logging - Subsequent Order not booked onto existing trip","Dominic Murphy <dmurphy@aptean.com>","Closed","On-hold","CTY",4,"4 - Low","2023-09-21T12:14:44","CTY-E2E","Bug",null,"Functional"]
[518292,"Calidus\\CTMS","CTY CTMS Vehicle Search - Customer Vehicles are showing NOT INSPECTED when they are.",null,"Closed","Installed on UAT","CTY",2,"3 - Medium","2023-09-21T12:33:27","CTY-E2E","Bug",null,"Functional",null,"CTMS ER044-083"]
[518297,"Calidus\\CTMS","CTY CTMS-EPOD Interface - Service jobs still being set as UNLOADING jobs","Susan Rose <srose@aptean.com>","Closed","On Test","CTY",4,"4 - Low","2023-09-21T12:55:07","CTY-E2E","Bug",null,"Functional"]
[518298,"Calidus\\CTMS","CTY CTMS ELUCID WEBSERVICE EXPORT - Doesn't include SERVICES section",null,"Closed",null,"CTY",2,"2 - High","2023-09-21T13:05:45","CTY-E2E","Bug",null,"Services Bug","No Fault found"]
[518536,"Calidus\\CTMS","CTY CTMS Planning screen - first entry into screen issues error",null,"Closed",null,"CTY",2,"3 - Medium","2023-09-22T09:55:30","CTY-E2E","Bug"]
[518589,"Calidus\\CTMS","CTY CTL Call Logging - Cancel/Delete order does not prompt for reason code",null,"Closed",null,"CTY",2,"3 - Medium","2023-09-22T11:47:33","CTY-E2E","Bug",null,"Missed Requirement","Missing function","CTMS ER044-092"]
[518591,"Calidus\\CTL","CTY CTL Call Logging - Services Supplied for Truck not filtering by tyre size",null,"Closed",null,"CTY",2,"2 - High","2023-09-22T11:53:24","CTY-E2E","Bug",null,null,"Design error","CTL 3.1.9, CTL 3.1.10"]
[518660,"Calidus\\CTMS","CTY CTMS Import - Tyres import fails.",null,"Closed",null,"CTY",2,"3 - Medium","2023-09-22T13:59:15","CTY-E2E","Bug",null,"Services Bug","Design error","CTMS ER044-084"]
[519149,"Calidus\\CTL","CTY CTL Vehicle Fleet Maintenance - Inspection action not shown.",null,"Closed",null,"CTY",2,"2 - High","2023-09-25T15:52:34","CTY-E2E","Bug",null,null,"Design error","CTL 3.1.10"]
[519157,"Calidus\\EPOD Device","CTY EPOD Device - Inspection Part Search doesn't show all of the tyres expected.",null,"Closed","On-hold","CTY",2,"2 - High","2023-09-25T16:06:00","CTY-E2E","Bug"]
[519173,"Calidus\\CTMS","CTY CTMS - EPOD Interface - Adding installs to fleet inspection is missing customer vehicle",null,"Closed",null,"CTY",2,"1 - Critical","2023-09-25T16:42:45","CTY-E2E","Bug",null,"Services Bug","Design constraint","CTMS ER044-083"]
[519363,"Calidus\\EPOD Device","CTY EPOD Customer Vehicle not populated on the records created from the android app.","Robert McGee <rmcgee@aptean.com>","Closed",null,"CTY",3,"4 - Low","2023-09-26T08:13:51","CTY-E2E","Bug",null,"Customization"]
[519555,"Calidus\\CTMS","CTY CTMS - EPOD web interface package is not working",null,"Closed",null,"CTY",2,"1 - Critical","2023-09-26T14:41:49","CTY-E2E","Bug"]
[519625,"Calidus\\CTL","CTY CTL Call Logging - Callback error issued when saving top-up transfer","Dominic Murphy <dmurphy@aptean.com>","Closed","On Test","CTY",4,"4 - Low","2023-09-26T15:50:12","CTY-E2E","Bug"]
[519862,"Calidus\\CTMS","CTY CTMS EPOD Interface - Outstanding inspection actions are not sent to EPOD","Dominic Murphy <dmurphy@aptean.com>","Closed","On-hold","CTY",4,"4 - Low","2023-09-27T09:11:26","CTY-E2E","Bug",null,"Functional"]
[519864,"Calidus\\CTMS","CTY CTMS - Booking job onto already existing job result sin trip end time being reset",null,"Closed","Installed on UAT","CTY",1,"2 - High","2023-09-27T09:22:57","CTY-E2E","Bug",null,"Functional","Program error","CTMS ER044-091"]
[519932,"Calidus\\EPOD Device","CTY EPOD Device - Inspections not sent back to server for scheduled callout",null,"Closed",null,"CTY",2,"2 - High","2023-09-27T11:54:08","CTY-E2E","Bug"]
[520004,"Calidus\\EPOD Admin","CTY EPOD - 17K Service Product Master records causes EPOD Device login to time out.",null,"Closed","On Test","CTY",3,"4 - Low","2023-09-27T13:50:28","CTY-E2E","Bug",null,"Performance"]
[520011,"Calidus\\CTL","CTY CTL Vehicle Fleet Maintenance screen showing vehicles requiring inspection and Actions incorrectly",null,"Closed",null,"CTY",1,"2 - High","2023-09-27T14:27:14","CTY-E2E","Bug",null,"Functional","Design error"]
[520014,"Calidus\\CTMS","CTY CTMS EPOD - CTMS Trip times incorrect","Tina Kinsella <tkinsella@aptean.com>","Closed","On Test","CTY",4,"4 - Low","2023-09-27T14:31:55","CTY-E2E","Bug",null,"Functional"]
[520055,"Calidus\\EPOD Device","CTY EPOD Device - Part Search for removal should show all products",null,"Closed",null,"CTY",1,"2 - High","2023-09-27T16:15:11","CTY-E2E","Bug",null,"Compatibility"]
[520185,"Calidus\\CTMS","CTY CTMS - Customer Vehicle Import fails",null,"Closed",null,"CTY",2,"2 - High","2023-09-28T08:13:54","CTY-E2E","Bug",null,"Services Bug","Design error","CTMS ER044-088"]
[520189,"Calidus\\CTL","520189 CTY CTL - FIA Report fixes",null,"Closed",null,"CTY",3,"3 - Medium","2023-09-28T08:30:07","CTY-E2E","Bug",null,"Functional","Design error"]
[520199,"Calidus\\PORTAL","CTY Portal - Can't upload news items to multiple groups",null,"Closed",null,"CTY",2,"3 - Medium","2023-09-28T08:40:13","CTY-E2E","Bug",null,"Functional","Design error","Patched"]
[520332,"Calidus\\CTMS","CTY CTMS EPOD Interface - Main address does not include Lat/Long",null,"Closed",null,"CTY",1,"2 - High","2023-09-28T11:16:32","CTY-E2E","Bug",null,"Functional","Program error","CTMS ER044-094"]
[520335,"Calidus\\CTMS","CTY CTMS-PORTAL TTM Interface - Orders still showing as part-delivered in Order Visibility","Susan Rose <srose@aptean.com>","Closed","Installed on UAT","CTY",2,"2 - High","2023-09-28T11:27:41","CTY-E2E","Bug",null,"Functional","Program error","CTMS ER044-094"]
[520451,"Calidus\\CTL","CTY CTL Call Logging - Fit Other displays all products from all depots",null,"Closed",null,"CTY",4,"3 - Medium","2023-09-28T15:25:49","CTY-E2E","Bug"]
[520469,"Calidus\\CTL","CTY CTL Call Logging - Fit Other / Fit COP issues",null,"Closed",null,"CTY",2,"3 - Medium","2023-09-28T15:57:27","CTY-E2E","Bug",null,"Functional","Design error","CTL: 3.01.15"]
[521007,"Calidus\\CTMS","CTY CTMS Customer/Cost Centre shows error when entering the screen",null,"Closed",null,"CTY",1,"1 - Critical","2023-09-29T08:37:28","CTY-E2E","Bug",null,"Functional","Datafix","CTMS ER044-087"]
[521432,"Calidus\\CTL","CTY CTL Call Logging - Fleet Inspection asks for position on van stock","Dominic Murphy <dmurphy@aptean.com>","Closed","On Test","CTY",4,"4 - Low","2023-10-02T13:52:17","CTY-E2E","Bug"]
[521910,"Calidus\\EPOD Device","CTY EPOD Device - EPL LOCATION not correctly set against EPOD_SERVICE_PRODUCT lines.",null,"Closed",null,"CTY",1,"1 - Critical","2023-10-03T15:30:36","CTY-E2E","Bug"]
[521914,"Calidus\\CTMS","CTY CTMS - Treat FAILED jobs as a cancellation message to outbound API.",null,"Closed",null,"CTY",1,"1 - Critical","2023-10-03T15:39:02","CTY-E2E","Bug",null,"Functional",null,"CTMS ER044-095"]
[521930,"Calidus\\EPOD Admin","CTY EPOD - Device picked up a trip for the wrong van","Susan Rose <srose@aptean.com>","Closed","On Test","CTY",2,"2 - High","2023-10-03T16:07:12","CTY-E2E","Bug"]
[522177,"Calidus\\EPOD Admin","CTY EPOD UDF Configuration - multiple changes",null,"Closed",null,"CTY",2,"2 - High","2023-10-04T08:36:58","CTY-E2E","Bug",null,"Setup","Implementation"]
[522359,"Calidus\\CTMS","CTY EPOD Device - Vehicle search produced many tyres ",null,"Closed",null,"CTY",2,"2 - High","2023-10-04T14:54:49","CTY-E2E","Bug",null,"Functional",null,"CTMS ER044-096"]
[523460,"Calidus\\EPOD Device","CTY EPOD/CTMS - Vehicle Search - Issue when known vehicle is searched.",null,"Closed",null,"CTY",1,"2 - High","2023-10-06T10:50:45","CTY-E2E","Bug"]
[523601,"Calidus\\CTMS","CTY CTMS EOD Interface - EPL_LOCATION does not update when returned from EPOD",null,"Closed",null,"CTY",1,"1 - Critical","2023-10-06T13:46:40","CTY-E2E","Bug"]
[524187,"Calidus\\CTMS","CTY CTMS EPOD - Trip doesn't close when closed on device","Dominic Murphy <dmurphy@aptean.com>","Closed","On Test","CTY",2,"3 - Medium","2023-10-09T15:59:52","CTY-E2E","Bug",null,"Functional"]
[524191,"Calidus\\CTMS","CTY Call Logging - Cancelling an order in CTL Call Logging should ask for and set Order Reason Codes","Paul Jones <pjones@aptean.com>","Closed","Installed on PRD","CTY",2,"3 - Medium","2023-10-09T16:02:47","CTY-UAT","Bug",null,"Functional","Missing function","CTMS ER045-027"]
[524427,"Calidus\\EPOD Device","CTY EPOD Device - Remove button on device prompts for removal details twice.","Dominic Murphy <dmurphy@aptean.com>","Closed","On Test","CTY",2,"3 - Medium","2023-10-10T10:20:42","CTY-E2E","Bug",null,null,"Program error (rework)","4.05.00.92"]
[524458,"Calidus\\EPOD Device","CTY EPOD Device - display a waiting message when waiting for results from part search","Dominic Murphy <dmurphy@aptean.com>","Closed","On Test","CTY",3,"4 - Low","2023-10-10T11:07:35","CTY-E2E","Bug",null,null,"Program error (rework)","4.05.00.93"]
[524462,"Calidus\\CTMS","CTY CTMS EPOD Interface - Tyre pressure and tread depth getting reset","Susan Rose <srose@aptean.com>","Closed","Installed on PRD","CTY",2,"3 - Medium","2023-10-10T11:30:58","CTY-E2E","Bug",null,"Functional",null,"CTMS ER045-004"]
[524474,"Calidus\\PORTAL","CTY PORTAL - Invoice not coming onto Portal from Elucid",null,"Closed",null,"CTY",1,"1 - Critical","2023-10-10T12:04:42","CTY-E2E","Bug"]
[524481,"Calidus\\CTMS","CTY CTMS Vehicle Search Webservice - returning inspection wrong.","Susan Rose <srose@aptean.com>","Closed","Installed on PRD","CTY",2,"3 - Medium","2023-10-10T12:24:22","CTY-E2E","Bug",{"$nulls":3},"CTMS ER045-004"]
[524532,"Calidus\\EPOD Device","CTY EPOD Device - Deleting a removal, then re-adding it - doesn't appear on the list","Dominic Murphy <dmurphy@aptean.com>","Closed","On Test","CTY",2,"3 - Medium","2023-10-10T14:38:44","CTY-E2E","Bug",null,null,"Program error (rework)","4.05.00.92"]
[524533,"Calidus\\CTL","CTY CTL Call Logging - Services for TRAILER type not showing ",null,"Closed",null,"CTY",2,"3 - Medium","2023-10-10T14:39:45","CTY-E2E","Bug",null,"Functional","Design error","CTL: 3.01.15"]
[524539,"Calidus\\CTMS","CTY CTMS - Install line TO_DELIVER quantity is wrong","Susan Rose <srose@aptean.com>","Closed","On Test","CTY",2,"1 - Critical","2023-10-10T14:47:59","CTY-E2E","Bug",null,"Services Bug","Design error"]
[524543,"Calidus\\CTL","CTY CTL - Call Logging - Nearest stock holding location - shows n/a ",null,"Closed",null,"CTY",2,"3 - Medium","2023-10-10T14:57:24","CTY-E2E","Bug",null,"Functional","Design error","CTL: 3.01.15"]
[524544,"Calidus\\CTMS","CTY CTMS API Export - COL sent after DEL","Tina Kinsella <tkinsella@aptean.com>","Closed","Installed on UAT","CTY",1,"2 - High","2023-10-10T14:58:57","CTY-E2E","Bug",null,"Functional","Design error","CTMS ER044-105"]
[524586,"Calidus\\CTMS","CTY CTMS EPOD Interface - Vehicle serviced at roadside should not change the location against that vehicle.","Dominic Murphy <dmurphy@aptean.com>","Closed","Installed on PRD","CTY",2,"3 - Medium","2023-10-10T16:39:40","CTY-UAT","Bug",null,"Functional",null,"CTMS ER045-017"]
[524589,"Calidus\\EPOD Device","CTY EPOD Device - No facility to cancel a service item (vehicle).","Susan Rose <srose@aptean.com>","Closed",null,"CTY",3,"3 - Medium","2023-10-10T16:51:00","CTY-E2E","Bug"]
[524609,"Calidus\\CTMS","CTY CTMS - Generate van stock line for every Fit New install","Susan Rose <srose@aptean.com>","Closed","On Test","CTY",1,"1 - Critical","2023-10-10T17:17:22","CTY-E2E","Bug",null,"Functional",null,"CTMS ER044-104"]
[525182,"Calidus\\CTMS","CTY CTMS API - Additional messages sent after order completed.","Dominic Murphy <dmurphy@aptean.com>","Closed","Installed on PRD","CTY",1,"3 - Medium","2023-10-12T08:38:27","CTY-E2E","Bug",null,"Functional",null,"CTMS ER045-003"]
[525198,"Calidus\\CTL","CTY CTL Call Logging - Can't raise a top-up transfer against a service-only job","Dominic Murphy <dmurphy@aptean.com>","Closed","On Test","Central Tyre",2,"3 - Medium","2023-10-12T09:00:56","CTY-E2E","Bug",null,"Services Bug"]
[525200,"Calidus\\CTL","CTY CTL Call Logging - Changing carrier on main screen doesn't change carriers on Booking tab","Susan Rose <srose@aptean.com>","Closed","On Test","CTY",2,"3 - Medium","2023-10-12T09:17:26","CTY-E2E","Bug",null,"Functional"]
[525350,"Calidus\\EPOD Device","CTY EPOD Device - Adding a new vehicle without an internet connection fails.","Susan Rose <srose@aptean.com>","Closed",null,"CTY",2,"3 - Medium","2023-10-12T13:38:57","CTY-E2E","Bug"]
[525358,"Calidus\\EPOD Device","CTY EPOD Device - No Cancel Vehicle button","Dominic Murphy <dmurphy@aptean.com>","Closed","On Test","CTY",2,"3 - Medium","2023-10-12T13:48:32","CTY-UAT","Bug",null,"Missed Requirement","Revised requirement"]
[525976,"Calidus\\CTMS","CTY Call Logging - Cannot create services only without a product","Susan Rose <srose@aptean.com>","Closed","Installed on UAT","CTY",2,"1 - Critical","2023-10-14T09:18:39","CTY-E2E","Bug",null,"Functional",null,"CTMS ER044-108"]
[525977,"Calidus\\CTL","CTY CTL Call Logging - Part Search shows Ratio as column title - should be Diameter.","Dominic Murphy <dmurphy@aptean.com>","Closed","On Test","CTY",4,"4 - Low","2023-10-14T11:02:30","CTY-E2E","Bug"]
[525979,"Calidus\\EPOD Admin","CTY EPOD Service Report - Footer doesn't look well aligned","Dominic Murphy <dmurphy@aptean.com>","Closed","On Test","CTY",3,"3 - Medium","2023-10-14T12:15:46","CTY-E2E","Bug"]
[533564,"Calidus\\EPOD Device","CTY EPOD Device - Provide list of vehicles that are on the service","Murray Middleton <jmiddleton@aptean.com>","Closed",null,"Central Tyres",3,"4 - Low","2023-11-08T14:07:59","CTY-E2E","User Story",null,null,"Revised requirement"]
[533567,"Calidus\\EPOD Device","CTY EPOD Device - Cancelled vehicle inspections can be edited on the device","Dominic Murphy <dmurphy@aptean.com>","Closed","On Test","CTY",2,"2 - High","2023-11-08T14:12:41","CTY-UAT","Bug",null,"Legacy","Program error (rework)","4.05.00.95"]
[533572,"Calidus\\EPOD Device","CTY EPOD Device - Load from yesterday can still be worked on today","Robert McGee <rmcgee@aptean.com>","Closed",null,"CTY",2,"2 - High","2023-11-08T14:20:46","CTY-UAT","Bug",null,null,"Missing function"]
[533682,"Calidus\\EPOD Device","CTY EPOD Device - Comments disappear from photobars","Paul Jones <pjones@aptean.com>","Closed","Ready for Rel","CTY",2,"2 - High","2023-11-08T17:58:01","CTY-UAT","Bug",null,null,"Design error"]
[545095,"Calidus\\CTMS","SCR-CTMS-02428249-05 - CTMS - Customer-Specific Tracking File","Carl Styles <cstyles@aptean.com>","Closed",null,"DHL Supply Chain Ltd",2,null,"2023-12-14T09:14:34",null,"User Story",528733,null,null,"CTMS ER046-045"]
[547083,"Calidus\\CTMS","STS - New Order screen shows no detail of an order when editing/viewing order","Paul Roscoe <proscoe@aptean.com>","Closed",null,"Stapletons",2,"3 - Medium","2023-12-21T14:38:27",null,"Bug",null,"Services Bug","Version/release control"]
[570824,"Calidus\\CTMS","Authority Ref not appearing on some jobs. UAT 213","Carl Styles <cstyles@aptean.com>","Closed","Installed on PRD","Central Tyre",2,"3 - Medium","2024-03-08T09:55:23","CTY-UAT2","Bug",null,"Functional",null,"CTMS ER045-093"]
[570826,"Calidus\\EPOD Device","Fleet Inspections - cannot add a new vehicle or lookup a vehicle in the mobile device - UAT 217","Robert McGee <rmcgee@aptean.com>","Closed",null,"Central Tyre",1,"1 - Critical","2024-03-08T10:01:48","CTY-UAT2","Bug",null,null,"Datafix"]
[576890,"Calidus\\EPOD Admin","CTY EPOD - Regroove and Notes not showing on service report","Tony Walker <twalker@aptean.com>","Closed","Ready for Rel","Central Tyre",2,"3 - Medium","2024-03-25T12:01:55","CTY-UAT2","Bug",null,null,"Program error (rework)"]
[579959,"Calidus\\EPOD Device","CTY UAT2 - Multiple phone numbers not splitting","Tony Walker <twalker@aptean.com>","Closed",null,"Central Tyres",2,"3 - Medium","2024-04-03T16:12:53","CTY-UAT2","Bug",null,null,"Revised requirement","4.05.01.06"]
[581511,"Calidus\\EPOD Admin","CTY - EPOD - Service Report - Removal reasons not showing","Susan Rose <srose@aptean.com>","Closed","On Test","Central Tyres",2,"2 - High","2024-04-09T08:30:46","CTY-UAT2","Bug",null,null,"Development"]
[583190,"Calidus\\CTL","CTY CTL Vehicle Fleet Maintenance - Edit Inspection Resolution Details not populating","Dominic Murphy <dmurphy@aptean.com>","Closed",null,"Central Tyres",2,"3 - Medium","2024-04-15T09:15:58","CTY-UAT2","Bug",null,null,"Development"]
[585174,"Calidus\\CTMS","First stop departure for AM/Night runs.","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapleton's Tyre Services Ltd",2,"2 - High","2024-04-19T12:52:25",null,"Bug",null,"Functional","Program error","CTMS ER046-009"]
[585175,"Calidus\\CTMS","Routes don't upload if there is no route end time","Susan Rose <srose@aptean.com>","Closed","On-hold","Stapletons",2,"2 - High","2024-04-19T12:53:57",null,"Bug",null,"Functional"]
[585176,"Calidus\\CTMS","Trips screen: Show on map","Carl Styles <cstyles@aptean.com>","Closed","Ready for Rel","Stapletons",2,"2 - High","2024-04-19T12:54:44",null,"Bug",null,"Functional","Version/release control","CTMS ER046-063 "]
[585177,"Calidus\\CTMS","Waterfall Screen: Sortation on new columns","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",2,"3 - Medium","2024-04-19T12:55:33",null,"Bug",null,"Usability","Design constraint","CTMS ER046-029"]
[585179,"Calidus\\CTMS","Resources - Vehicles screen - can't assign to carrier.","Tina Kinsella <tkinsella@aptean.com>","Closed","On-hold","Stapletons",2,"3 - Medium","2024-04-19T13:02:27",null,"Bug",null,"Functional"]
[585182,"Calidus\\CTMS","Resource Maintenance/Drivers/Diary Exceptions - problems entering exception","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",2,"3 - Medium","2024-04-19T13:08:07",null,"Bug",null,"Functional","Design error","CTMS ER046-034"]
[585183,"Calidus\\CTMS","BDM screen/Shift Patterns - spurious error","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",2,"3 - Medium","2024-04-19T13:10:17",null,"Bug",null,"Functional","Design error","CTMS ER046-037"]
[585186,"Calidus\\CTMS","Resource Availability Allocation – problems with Save","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",2,"3 - Medium","2024-04-19T13:15:43",null,"Bug",null,"Functional","Design error","CTMS ER046-036"]
[585187,"Calidus\\CTMS","Some parameters can’t be set from the screen","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",2,"2 - High","2024-04-19T13:17:04",null,"Bug",null,"Legacy","Datafix","CTMS ER046-029"]
[585190,"Calidus\\CTMS","Location windows can't be viewed or edited in CTMS","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",2,"3 - Medium","2024-04-19T13:22:33",null,"Bug",null,"Missed Requirement","Design error","CTMS ER046-022"]
[585191,"Calidus\\CTMS","Location EXT Ref and Paragon ID can't be seen on the Locations Maintenance screen","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",2,"3 - Medium","2024-04-19T13:23:49",null,"Bug",null,"Functional","Design error","CTMS ER046-022"]
[585192,"Calidus\\CTMS","Locations Maintenance - Show on map displays an error in the popup tab window","Susan Rose <srose@aptean.com>","Closed","On-hold","Stapletons",2,"2 - High","2024-04-19T13:26:02",null,"Bug"]
[585193,"Calidus\\CTMS","Flexipod flags not configurable in the system","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",2,"3 - Medium","2024-04-19T13:34:12",null,"Bug",null,"Functional","Missing function","CTMS ER046-038"]
[585198,"Calidus\\CTMS","ORS reports not in sync","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",2,"3 - Medium","2024-04-19T14:12:46",null,"Bug",null,"Functional",null,"CTMS ER046-039"]
[585205,"Calidus\\CTMS","Stapletons Scheduling engine - doesn't set the trailer type against the trip","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",2,"3 - Medium","2024-04-19T14:22:29",null,"Bug",null,null,"Program error","CTMS ER046-017"]
[585207,"Calidus\\CTMS","Planning screen opens the old Orders screen - should be the new Orders screen","Susan Rose <srose@aptean.com>","Closed","Ready for Rel","Stapletons",2,"3 - Medium","2024-04-19T14:26:54",null,"Bug",null,"Functional"]
[585210,"Calidus\\CTMS","Fixed Routes maintenance screen - search criteria resets","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",2,"3 - Medium","2024-04-19T14:37:43",null,"Bug",null,"Functional","Program error","CTMS ER046-010"]
[585234,"Calidus\\CTMS","Waterfall screen - Alloc Resources button and menu option call different screens","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",2,"3 - Medium","2024-04-19T15:28:11",null,"Bug",null,"Functional","Program error","CTMS ER046-016"]
[586380,"Calidus\\EPOD Admin","CTY - PROD - EPOD - UDF Screen can't edit some UDF forms","Roger Egdell <regdell@aptean.com>","Closed",null,"Central Tyres",2,"3 - Medium","2024-04-23T16:55:09","CTY-PRD","Bug",null,null,"Program error (rework)"]
[586888,"Calidus\\CTMS","Resources Screen - Load Rates - can't enter multiple DU type rates.","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons Tyre Services",2,"3 - Medium","2024-04-24T10:53:44",null,"Bug",null,"Services Bug","Design error","CTMS ER046-034"]
[591663,"Calidus\\CTMS","Polar Speed - Order Services doesn't work as expected","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polar Speed",2,"3 - Medium","2024-05-03T10:36:48",null,"Bug",null,"Functional","Program error","CTMS ER046-032"]
[614486,"Calidus\\CTMS","CTMS - STSTPRD - Countries - Can't enter a non-working day NWD ","Tony Walker <twalker@aptean.com>","Closed",null,"Stapletons",2,"3 - Medium","2024-07-01T12:29:20",null,"Bug"]
[614901,"Calidus\\CTMS","CTMS - STSTPRD - Location References don't display names correctly","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",2,"3 - Medium","2024-07-02T11:30:10",null,"Bug",null,"Regression","Design constraint","CTMS ER046-044"]
[614903,"Calidus\\CTMS","CTMS - STSTPRD - Pay On Delivery/Collect Casings/Network Available flags not visible","Susan Rose <srose@aptean.com>","Closed",null,"Stapletons",2,"3 - Medium","2024-07-02T11:43:30",null,"Bug",null,"Regression"]
[616806,"Calidus\\CTMS","SCR-CTMS-03557646-19 Allow lookup of route numbers in Planning screen","Carl Styles <cstyles@aptean.com>","Closed",null,"Stapletons",2,null,"2024-07-09T10:17:19","STS TS3RDX","User Story",616801,null,null,"CTMS ER047-029"]
[616827,"Calidus\\CTMS","SCR-CTMS-03557646-04 Transfer Order - Trip Lookup to show route","Carl Styles <cstyles@aptean.com>","Closed",null,"Stapletons",2,null,"2024-07-09T10:48:06","STS TS3RDX","User Story",616801,null,null,"CTMS ER047-021"]
[616853,"Calidus\\CTMS","SCR-CTMS-03557646-05: Multi-select and set ACCEPTED status from Waterfall screen.","Carl Styles <cstyles@aptean.com>","Closed",null,"Stapletons",2,null,"2024-07-09T11:19:21","STS TS3RDX","User Story",616801,null,null,"CTMS ER047-016"]
[616866,"Calidus\\CTMS","SCR-CTMS-03557646-06 Attach Exception Reports to the Waterfall screen","Carl Styles <cstyles@aptean.com>","Closed",null,"Stapletons",2,null,"2024-07-09T11:36:59","STS TS3RDX","User Story",616801,null,null,"CTMS ER047-015"]
[616907,"Calidus\\CTMS","SCR-CTMS-03557646-03 Specific data reports, summing Tyres only","Carl Styles <cstyles@aptean.com>","Closed",null,"Stapletons",2,null,"2024-07-09T12:18:41","STS TS3RDX","User Story",616801,null,null,"CTMS ER047-019"]
[617057,"Calidus\\CTMS","SCR-CTMS-03557646-07 Allow drill-down from Waterfall to Planning","Carl Styles <cstyles@aptean.com>","Closed",null,"Stapletons",2,null,"2024-07-09T14:08:01","STS TS3RDX","User Story",616801]
[619205,"Calidus\\CTMS","SCR-CTMS-03557646-02 Trip Prefix change from TMP (configurable)","Carl Styles <cstyles@aptean.com>","Closed",null,"Stapletons",2,null,"2024-07-16T08:04:00","STS TS3RDX","User Story",616801]
[619888,"Calidus\\CTMS","SCR-CTMS-03557646-08 Add route end time to Route Header screen","Carl Styles <cstyles@aptean.com>","Closed",null,"Stapletons",2,null,"2024-07-17T09:29:40","STS TS3RDX","User Story",616801,null,null,"CTMS ER047-017"]
[619949,"Calidus\\CTMS","SCR-CTMS-03557646-09 Add route end time to ORS report on routes","Carl Styles <cstyles@aptean.com>","Closed",null,"Stapletons",2,null,"2024-07-17T09:51:09","STS TS3RDX","User Story",616801,null,null,"CTMS ER047-018"]
[620535,"Calidus\\CTMS","SCR-CTMS-03557646-13 Get price on orders TS 3.5","Dominic Murphy <dmurphy@aptean.com>","Closed",null,"Stapletons",2,null,"2024-07-18T09:10:38","STS TS3RDX","User Story",616801,null,null,"CTMS ER047-040"]
[624211,"Calidus\\CTMS","STSTPRD - Paragon Strategic Interface - outstanding issues - Backlog","Susan Rose <srose@aptean.com>","Closed",null,"Stapletons",2,"3 - Medium","2024-07-30T13:58:11","STS TS4","Bug"]
[630406,"Calidus\\CTL","CTYTPRD CTL Error when updating order","Paul Roscoe <proscoe@aptean.com>","Closed",null,"Central Tyres",2,"3 - Medium","2024-08-16T09:24:54","CTY-PRD","Bug",null,"Services Bug","RCA - Root Cause Analysis"]
[705530,"Calidus\\CTMS","Scheduling Engine not working in STSTTST2","Carl Styles <cstyles@aptean.com>","Closed","Ready for Rel","Stapletons",2,"2 - High","2025-03-05T14:26:12","STS TS3RDX","Bug",null,null,"Datafix"]
[706497,"Calidus\\CTL","EPOD CTYPRD - Resource Activity report isn’t working","Roger Egdell <regdell@aptean.com>","Closed",null,"CTY",2,"3 - Medium","2025-03-07T09:46:12","CTY-PRD","Bug"]
[708331,"Calidus\\CTMS","CTMS STSTTST2 Carry Forward Route/Trip Lookup needs work","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",2,"3 - Medium","2025-03-12T08:30:48","STS TS3RDX","Bug",null,"Functional",null,"CTMS ER047-041"]
[708335,"Calidus\\CTMS","CTMS STSTTST2 Carry Forward doesn't carry forward a scheduled order.","Carl Styles <cstyles@aptean.com>","Closed","Ready for Rel","Stapletons",2,"3 - Medium","2025-03-12T08:33:33","STS TS3RDX","Bug",null,"Functional"]
[708338,"Calidus\\CTMS","CTMS STSTTST2 Carry Forward - trip created from route needs work","Carl Styles <cstyles@aptean.com>","Closed","Ready for Rel","Stapletons",2,"3 - Medium","2025-03-12T08:35:19","STS TS3RDX","Bug",null,"Functional"]
[708339,"Calidus\\CTMS","CTMS STSTTST2 Planning - Unscheduling an order does not set the manual planning flag.","Carl Styles <cstyles@aptean.com>","Closed","Ready for Rel","Stapletons",2,"3 - Medium","2025-03-12T08:38:58","STS TS3RDX","Bug",null,"Functional"]
[708346,"Calidus\\CTMS","CTMS STSTTST2 Depot Sweep - checks 90 days into the future.","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",2,"3 - Medium","2025-03-12T08:45:56","STS TS3RDX","Bug",null,null,"Development","CTMS ER047-045"]
[708350,"Calidus\\CTMS","CTMS STSTTST2 Depot Sweep - The COLLECT_DESK/RESCHEDULE process picked up a manually planned incomplete order.","Carl Styles <cstyles@aptean.com>","Closed","Ready for Rel","Stapletons",2,"2 - High","2025-03-12T08:49:07","STS TS3RDX","Bug",null,"Functional","Development"]
[708351,"Calidus\\CTMS","CTMS STSTTST2 Scheduling Engine scheduled an order to a schedule when past the cutoff","Roger Egdell <regdell@aptean.com>","Closed","Test Fail","Stapletons",2,"2 - High","2025-03-12T08:50:46","STS TS3RDX","Bug",null,null,"Development"]
[708353,"Calidus\\CTMS","CTMS STSTTST2 Route Maint Screen needs loc usage records when it shouldn't","Carl Styles <cstyles@aptean.com>","Closed","Ready for Rel","Stapletons",2,"3 - Medium","2025-03-12T08:52:40","STS TS3RDX","Bug",null,"Functional","Unable to replicate"]
[708354,"Calidus\\CTMS","CTMS STSTTST2 Depot Sweep - Reschedule leaves empty trips behind","Carl Styles <cstyles@aptean.com>","Closed","Ready for Rel","Stapletons",2,"3 - Medium","2025-03-12T08:54:26","STS TS3RDX","Bug",null,null,"Development"]
[716621,"Calidus\\CTMS","CTMS STSTTST2 - Scheduler sets order to SCHED_DEL","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",2,"3 - Medium","2025-03-31T15:46:06","STS TS3RDX","Bug",null,"Functional","Program error (rework)","CTMS ER047-052"]
[716848,"Calidus\\CTMS","CTMS STSTTST2 Rebooking an order leaves original order as REBOOK_REQUIRED","Carl Styles <cstyles@aptean.com>","Closed","Installed on PRD","Stapletons",2,"3 - Medium","2025-04-01T09:32:55","STS TS3RDX","Bug",null,"Functional","Program error (rework)","CTMS ER047-051"]
[718133,"Calidus\\CTMS","CTMS STSTTST2 - Scheduler sets order to SCHED_DEL","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Stapletons",1,"2 - High","2025-04-03T11:07:10","STS TS3RDX","Bug",708331,"Functional","Program error (rework)","CTMS ER047-055"]
[718139,"Calidus\\CTMS","SCR-CTMS-03557646-05: Multi-select and set ACCEPTED status from Waterfall screen.",null,"Closed",null,"Stapletons",3,"3 - Medium","2025-04-03T11:48:41","STS TS3RDX","Bug",616853,"Functional","Systems software fault"]
[718271,"Calidus\\CTMS","CTMS STSTTST2 - Rebook from Debrief hangs the system","Carl Styles <cstyles@aptean.com>","Closed","Ready for Rel","Stapletons",2,"2 - High","2025-04-03T15:02:01","STS TS3RDX","Bug",645363,"Functional","Program error (rework)"]
[718681,"Calidus\\CTMS","CTMS STSTTST2 Scheduler schedules on wrong day","Carl Styles <cstyles@aptean.com>","Closed","Ready for Rel","Stapletons",1,"2 - High","2025-04-04T08:55:31","STS TS3RDX","Bug",718133,"Functional","Program error (rework)"]
[719843,"Calidus\\CTMS","CTMS STSTPRD Browserless needs updating",null,"Closed",null,"Stapletons",2,"3 - Medium","2025-04-08T12:37:49","STS TS3RDX","Bug",null,"Compatibility"]
[729162,"Calidus\\PORTAL","PORTAL PDSTTST - Order amendment didn't create order items",null,"Closed","Installed on UAT","Polar Speed",2,"3 - Medium","2025-05-07T10:12:34","PS-POT1","Bug",620914,"Functional","Program error (rework)","11.01.020"]
[729295,"Calidus\\CTMS","CTMS PSDTTST Polar Speed PDF label has some issues","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polar Speed",2,"3 - Medium","2025-05-07T14:58:29","PS-POT1","Bug",620870,"Functional","Development","CTMS ER047-083"]
[738219,"Calidus\\EPOD Device","CTYTPRD EPOD Device - On device removals not defaulting","Dominic Murphy <dmurphy@aptean.com>","New","For Investigation","Central Tyre",2,"3 - Medium","2025-05-28T15:45:04","CTY-PRD","Bug"]
[738223,"Calidus\\EPOD Device","CTYTPRD EPOD Device - Show quantities of stock on part search","Harj Lasher <hlasher@aptean.com>","New","For Investigation","Central Tyre",2,"3 - Medium","2025-05-28T15:46:56","CTY-PRD","Bug"]
[738228,"Calidus\\EPOD Device","CTYTPRD EPOD Device - Device doesn't save enough","Harj Lasher <hlasher@aptean.com>","New","For Investigation","Central Tyre",2,"3 - Medium","2025-05-28T15:49:29","CTY-PRD","Bug"]
[738232,"Calidus\\CTL","CTYTPRD CTL - FIA report showing work completed the wrong way round.",null,"Closed",null,"Central Tyre",2,"3 - Medium","2025-05-28T15:52:59","CTY-PRD","Bug",null,"Functional","No Fault found"]
[738233,"Calidus\\CTL","CTYTPRD CTL - FIA Report selecting data incorrectly","Graham Rothwell <grothwell@aptean.com>","Active","On-hold","Central Tyre",2,"3 - Medium","2025-05-28T15:55:06","CTY-PRD","Bug",null,"Functional"]
[738238,"Calidus\\CTL","CTYTPRD CTL Vehicle Fleet Maintenance Screen bugs","Carl Styles <cstyles@aptean.com>","Closed","For Investigation","Central Tyre",2,"3 - Medium","2025-05-28T16:03:37","CTY-PRD","Bug",null,"Functional"]
[738239,"Calidus\\CTMS","CTYTPRD CTMS Vehicle added to wrong location","Graham Rothwell <grothwell@aptean.com>","Active","Investigating","Central Tyre",3,"3 - Medium","2025-05-28T16:05:16","CTY-PRD","Bug",null,"Functional"]
[738241,"Calidus\\CTL","CTYTPRD CTL Maps section bugs","Roger Egdell <regdell@aptean.com>","Closed","Ready for Rel","CTY",2,"3 - Medium","2025-05-28T16:09:12","CTY-PRD","Bug",null,"Functional","Development","CTL 3.1.55"]
[738242,"Calidus\\CTL","CTYTPRD CTL Login error","Graham Rothwell <grothwell@aptean.com>","New","For Investigation","Central Tyre",2,"3 - Medium","2025-05-28T16:10:49","CTY-PRD","Bug"]
[747000,"Calidus\\CTMS","CTMS PSDTTST Reason Code Maintenance Action is missing","Tina Kinsella <tkinsella@aptean.com>","Closed","Ready for Rel","Polar Speed",1,"1 - Critical","2025-06-24T08:31:31","PS-POT4","Bug",620876,"Functional","Program error (rework)"]
[747259,"Calidus\\CTMS","CTMS PDSTTST Quarantine items not being created.","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polar Speed",1,"1 - Critical","2025-06-24T10:46:37","PS-POT4","Bug",620877,"Functional","Program error (rework)","CTMS ER047-110"]
[749034,"Calidus\\WMS 810","CWMS WMSDEV Despatch Confirmation bugs","Carl Styles <cstyles@aptean.com>","New","For Investigation","Internal",3,"3 - Medium","2025-06-25T11:10:27",null,"Bug",null,"User Interface"]
[749404,"Calidus\\CTMS","PSDTTST CTMS Quarantine admin screen issues","Tina Kinsella <tkinsella@aptean.com>","Closed","Being programmed","Polar Speed",1,"2 - High","2025-06-26T10:41:48","PS-POT4","Bug",null,"Functional","Development"]
[752225,"Calidus\\PORTAL","CTYLIVE Portal language and display fields issues",null,"Closed",null,"Central Tyres",2,"3 - Medium","2025-07-02T14:28:26","CTY-PRD","Bug",null,"Functional"]
[753162,"Calidus\\CTMS","PSDTTST CTMS Quarantine Admin error","Tina Kinsella <tkinsella@aptean.com>","Active","For Investigation","Polarspeed",2,"3 - Medium","2025-07-04T10:52:49","PS-POT4","Bug",620877,"Functional","Development"]
[753169,"Calidus\\CTMS","PSDTTST CTMS Quarantine Admin - Further Errors","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polarspeed",2,"3 - Medium","2025-07-04T11:04:36","PS-POT4","Bug",620877,"Functional",null,"CTMS ER047-125"]
[755924,"Calidus\\Bay Diary","PODWQA Aps need updating","Roger Egdell <regdell@aptean.com>","New","For Investigation","Port of Dover",3,"3 - Medium","2025-07-14T09:08:50","POD SAAS","Bug",null,"Deployment"]
[755927,"Calidus\\Bay Diary","PODWQA Port of Dover Apps need fixed and updates","Roger Egdell <regdell@aptean.com>","New","For Investigation","Port of Dover",3,"3 - Medium","2025-07-14T09:26:00","POD SAAS","Bug"]
[756091,"Calidus\\MCS","PSDTTST MCS - Quarantine reason codes not showing in MCS","Roger Egdell <regdell@aptean.com>","New","For Investigation","Polarspeed",2,"3 - Medium","2025-07-14T15:06:32","PS-POT4","Bug"]

{"sheet":"Analysis","index":1,"n_rows":52,"n_cols":12,"rows_kept":52}
["Total Bugs"]
["Row Labels","Status Count","Status %"]
["Active",3,{"v":0.017543859649122806,"d":"1.75%"}]
["Closed",160,{"v":0.935672514619883,"d":"93.57%"}]
["New",8,{"v":0.04678362573099415,"d":"4.68%"}]
["Grand Total",171,{"v":1,"d":"100.00%"}]
[]
[]
["Bugs by Severity",{"$nulls":4},"Bugs by Priority"]
["State","(All)",{"$nulls":3},"State","(All)"]
[]
["Row Labels","Severity Count","Severity %",null,null,"Row Labels","Priority Count","Priority %"]
["1 - Critical",18,{"v":0.1125,"d":"11.25%"},null,null,1,20,{"v":0.11695906432748537,"d":"11.70%"}]
["2 - High",39,{"v":0.24375,"d":"24.38%"},null,null,2,125,{"v":0.7309941520467836,"d":"73.10%"}]
["3 - Medium",87,{"v":0.54375,"d":"54.38%"},null,null,3,14,{"v":0.08187134502923976,"d":"8.19%"}]
["4 - Low",16,{"v":0.1,"d":"10.00%"},null,null,4,12,{"v":0.07017543859649122,"d":"7.02%"}]
["(blank)",null,{"v":0,"d":"0.00%"},null,null,"Grand Total",171,{"v":1,"d":"100.00%"}]
["Grand Total",160,{"v":1,"d":"100.00%"}]
[]
["Bugs by System"]
["State","(All)"]
[]
["Systems","System Count","System %"]
["Calidus\\CTL",29,{"v":0.1695906432748538,"d":"16.96%"}]
["Calidus\\CTMS",100,{"v":0.5847953216374269,"d":"58.48%"}]
["Calidus\\EPOD Admin",9,{"v":0.05263157894736842,"d":"5.26%"}]
["Calidus\\EPOD Device",25,{"v":0.14619883040935672,"d":"14.62%"}]
["Calidus\\PORTAL",4,{"v":0.023391812865497075,"d":"2.34%"}]
["Calidus\\WMS 810",1,{"v":0.005847953216374269,"d":"0.58%"}]
["Calidus\\Bay Diary",2,{"v":0.011695906432748537,"d":"1.17%"}]
["Calidus\\MCS",1,{"v":0.005847953216374269,"d":"0.58%"}]
["Grand Total",171,{"v":1,"d":"100.00%"}]
[]
["Root Cause Analysis"]
["By Bug Type",{"$nulls":4},"By Fault",{"$nulls":4},"By Parent"]
["RCA","Count of Bug Type","%",null,null,"RCA","Count of Fault","%",null,null,"Row Labels","Count of Parent"]
["(blank)",null,{"v":0,"d":"0.00%"},null,null,"(blank)",null,{"v":0,"d":"0.00%"},null,null,528733,1]
["Functional",76,{"v":0.7450980392156863,"d":"74.51%"},null,null,"Program error",13,{"v":0.14772727272727273,"d":"14.77%"},null,null,616801,10]
["Services Bug",11,{"v":0.10784313725490197,"d":"10.78%"},null,null,"Design error",22,{"v":0.25,"d":"25.00%"},null,null,616853,1]
["Missed Requirement",3,{"v":0.029411764705882353,"d":"2.94%"},null,null,"Missing function",7,{"v":0.07954545454545454,"d":"7.95%"},null,null,620870,1]
["Customization",1,{"v":0.00980392156862745,"d":"0.98%"},null,null,"Program error (rework)",16,{"v":0.18181818181818182,"d":"18.18%"},null,null,620876,1]
["Performance",1,{"v":0.00980392156862745,"d":"0.98%"},null,null,"Design constraint",4,{"v":0.045454545454545456,"d":"4.55%"},null,null,620877,3]
["Compatibility",2,{"v":0.0196078431372549,"d":"1.96%"},null,null,"Unable to replicate",2,{"v":0.022727272727272728,"d":"2.27%"},null,null,620914,1]
["Setup",1,{"v":0.00980392156862745,"d":"0.98%"},null,null,"No Fault found",2,{"v":0.022727272727272728,"d":"2.27%"},null,null,645363,1]
["Legacy",2,{"v":0.0196078431372549,"d":"1.96%"},null,null,"Datafix",4,{"v":0.045454545454545456,"d":"4.55%"},null,null,708331,1]
["Usability",1,{"v":0.00980392156862745,"d":"0.98%"},null,null,"Implementation",1,{"v":0.011363636363636364,"d":"1.14%"},null,null,718133,1]
["Regression",2,{"v":0.0196078431372549,"d":"1.96%"},null,null,"Revised requirement",3,{"v":0.03409090909090909,"d":"3.41%"},null,null,"(blank)"]
["User Interface",1,{"v":0.00980392156862745,"d":"0.98%"},null,null,"Version/release control",2,{"v":0.022727272727272728,"d":"2.27%"},null,null,"Grand Total",21]
["Deployment",1,{"v":0.00980392156862745,"d":"0.98%"},null,null,"Development",10,{"v":0.11363636363636363,"d":"11.36%"}]
["Grand Total",102,{"v":1,"d":"100.00%"},null,null,"RCA - Root Cause Analysis",1,{"v":0.011363636363636364,"d":"1.14%"}]
[{"$nulls":5},"Systems software fault",1,{"v":0.011363636363636364,"d":"1.14%"}]
[{"$nulls":5},"Grand Total",88,{"v":1,"d":"100.00%"}]