{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["DevOps Bugs","Analysis"],"not_rendered":{"pivot_tables":7},"read":"whole","date_system":"1900"}

{"sheet":"DevOps Bugs","index":0,"n_rows":85,"n_cols":16,"rows_kept":85}
["ID","Area Path","Title","Assigned To","State","Sub state","Customer","Priority","Severity","Created Date","Tags","Work Item Type","Parent","Bug Type","Fault","Hotfix in Release"]
[759291,"Calidus\\CTMS","Location opening windows Default Parameter (SCR-61)","Simon Eland <seland@aptean.com>","Active","On Test","Polarspeed",2,"3 - Medium","2025-07-23T12:53:25","PS-POT2","Bug",620896,"Functional","Program error (rework)","CTMS ER047-141"]
[758750,"Calidus\\CTMS","Automatic Rebooking REBOOK_REQUIRED Issue (SCR-60)","Roger Egdell <regdell@aptean.com>","New","For Investigation","Polarspeed",2,"3 - Medium","2025-07-22T11:20:25","PS-POT4","Bug",620894,"Functional","Program error (rework)"]
[758573,"Calidus\\CTMS","Paragon Interface Missing Items (SCR-64)","Tina Kinsella <tkinsella@aptean.com>","Active","On-hold","Polarspeed",2,"3 - Medium","2025-07-22T07:37:50","PS-POT2","Bug",620897,"Functional","Program error (rework)"]
[757188,"Calidus\\MCS","MCS Pallet Build Issue (SCR-15)","Roger Egdell <regdell@aptean.com>","New","For Investigation","Polarspeed",2,"3 - Medium","2025-07-16T18:20:09","PS-POT3","Bug",620903,"Functional","Program error (rework)"]
[756091,"Calidus\\MCS","PSDTTST MCS - Quarantine reason codes not showing in MCS","Roger Egdell <regdell@aptean.com>","New","For Investigation","Polarspeed",2,"3 - Medium","2025-07-14T15:06:32","PS-POT4","Bug",null,"Functional"]
[755678,"Calidus\\CTMS","Automatic Rebooking Max No of Rebooks Issue (SCR-60)","Simon Eland <seland@aptean.com>","Active","On Test","Polarspeed",2,"3 - Medium","2025-07-11T09:29:17","PS-POT4","Bug",620894,"Functional","Missing function","CTMS ER047-138"]
[755677,"Calidus\\CTMS","Automatic Rebooking Issue (SCR-60)","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polarspeed",2,"3 - Medium","2025-07-11T09:26:08","PS-POT4","Bug",620894,"Functional","Program error (rework)","CTMS ER047-135"]
[755667,"Calidus\\CTMS","test",null,"Closed",null,null,2,"3 - Medium","2025-07-11T08:42:14","PS-POT4","Bug",null,null,"Implementation"]
[754642,"Calidus\\MCS","MCS Pallet Build / Receipt Issue (SCR-15)","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polarspeed",2,"3 - Medium","2025-07-09T11:13:32","PS-POT3","Bug",null,"Functional","Program error (rework)","MCS"]
[753491,"Calidus\\CTMS","Polarspeed PDF Label","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polarspeed",3,"3 - Medium","2025-07-07T10:53:46","PS-POT1; PS-POT3","Bug",null,"Functional","Program error (rework)","CTMS ER047-124"]
[753169,"Calidus\\CTMS","PSDTTST CTMS Quarantine Admin - Further Errors","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polarspeed",2,"3 - Medium","2025-07-04T11:04:36","PS-POT4","Bug",620877,"Functional","Program error (rework)","CTMS ER047-125"]
[753162,"Calidus\\CTMS","PSDTTST CTMS Quarantine Admin error","Tina Kinsella <tkinsella@aptean.com>","Active","For Investigation","Polarspeed",2,"3 - Medium","2025-07-04T10:52:49","PS-POT4","Bug",620877,"Functional","Version/release control","CTMS ER047-140"]
[752908,"Calidus\\MCS","Add and sort by drop number in despatch (SCR-28)","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polarspeed",2,"3 - Medium","2025-07-03T17:28:31","PS-POT3","Bug",620907,"Functional","Program error (rework)","CTMS ER047-133"]
[752710,"Calidus\\CTMS","Polarspeed Labels","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2025-07-03T11:28:42","PS-POT1","User Story",{"$nulls":3},"CTMS ER047-121"]
[752216,"Calidus\\MCS","Despatch Confirmation Scan of vehicle compartment. (SCR-26)","Carl Styles <cstyles@aptean.com>","Closed","Ready for Rel","Polarspeed ",2,"3 - Medium","2025-07-02T14:10:16","PS-POT3","Bug",620906,"Setup","User error"]
[751231,"Calidus\\MCS","Scan location after scanning item in Receipt and Damages process. (SCR-17)","Manjuladevi Mariappan <mm@aptean.com>","New","For Investigation","Polarspeed",2,"3 - Medium","2025-07-01T12:56:09","PS-POT3","Bug",620904,"Functional","Missing function"]
[749404,"Calidus\\CTMS","PSDTTST CTMS Quarantine admin screen issues","Tina Kinsella <tkinsella@aptean.com>","Closed","Being programmed","Polar Speed",1,"2 - High","2025-06-26T10:41:48","PS-POT4","Bug",null,"Functional","Development"]
[747259,"Calidus\\CTMS","CTMS PDSTTST Quarantine items not being created.","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polar Speed",1,"1 - Critical","2025-06-24T10:46:37","PS-POT4","Bug",620877,"Functional","Program error (rework)","CTMS ER047-110"]
[747000,"Calidus\\CTMS","CTMS PSDTTST Reason Code Maintenance Action is missing","Tina Kinsella <tkinsella@aptean.com>","Closed","Ready for Rel","Polar Speed",1,"1 - Critical","2025-06-24T08:31:31","PS-POT4","Bug",620876,"Functional","Program error (rework)"]
[746352,"Calidus\\MCS","MCS Issues","Roger Egdell <regdell@aptean.com>","New","For Investigation","Polarspeed",2,"3 - Medium","2025-06-20T16:56:49","PS-POT3","Bug"]
[744452,"Calidus\\CTMS","Order not being picked up by Paragon trigger","Carl Styles <cstyles@aptean.com>","Closed",null,"Polarspeed",2,"3 - Medium","2025-06-17T06:39:22","PS-POT2","Bug",null,"Functional","User error"]
[743790,"Calidus\\CTMS","Manual Schedule set to Y for orders created by CSV Order Import","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polarspeed",2,"3 - Medium","2025-06-13T12:45:08","PS-POT1","Bug",null,"Functional","Program error (rework)","CTMS ER047-106"]
[741314,"Calidus\\CTMS","EDI TripOrderXML - order status INVALID","Tina Kinsella <tkinsella@aptean.com>","Closed","For Investigation","Polarspeed",2,"3 - Medium","2025-06-06T10:41:00","PS-POT1","Bug",null,"Setup","User error"]
[741304,"Calidus\\CTMS","WebService TripOrderXML not using received Item Id value","Simon Eland <seland@aptean.com>","Active","For Investigation","Polarspeed",2,"3 - Medium","2025-06-06T10:25:37","PS-POT1","Bug",null,"Services Bug","Program error"]
[741290,"Calidus\\CTMS","Manual Order Entry - Original Del Type value incorrect","Simon Eland <seland@aptean.com>","Closed","For Investigation","Polarspeed",2,"3 - Medium","2025-06-06T10:09:40","PS-POT1","Bug",null,"Setup","User error"]
[741280,"Calidus\\PORTAL","Portal Order Entry amend delivery date","Graham Rothwell <grothwell@aptean.com>","Active",null,"Polarspeed",2,null,"2025-06-06T09:54:58","PS-POT1","User Story"]
[741277,"Calidus\\CTMS","PDF and ZPL labels displaying the incorrect symbol","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polarspeed ",2,"3 - Medium","2025-06-06T09:43:39","PS-POT1","Bug",null,"Functional","Program error (rework)","CTMS ER047-103"]
[741264,"Calidus\\PORTAL","Portal Order Entry submission summary page","Simon Eland <seland@aptean.com>","Active",null,"Polarspeed",2,null,"2025-06-06T09:24:19","PS-POT1","User Story",{"$nulls":3},"11.01.023"]
[736388,"Calidus\\CTMS","Import Derive Delivery Window (SCR-10)","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polarspeed",1,"3 - Medium","2025-05-22T14:32:33","PS-POT1","Bug",null,"Functional","Design error","CTMS ER047-090"]
[735892,"Calidus\\CTMS","CSV Order Import - Set From Location (SCR-10)","Carl Styles <cstyles@aptean.com>","Closed","Ready for Rel","Polarspeed",2,"3 - Medium","2025-05-21T11:59:35","PS-POT1","Bug",null,"Functional"]
[734074,"Calidus\\CTMS","Extend the length of the addresses for TI orders","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polarspeed",1,"3 - Medium","2025-05-16T08:58:37","PS-POT1","Bug",620871,null,"Design constraint","CTMS ER047-084"]
[729433,"Calidus\\CTMS","Issue with WebService TripOrderXML import process","Paul Roscoe <proscoe@aptean.com>","Closed","For Investigation","Polar Speed",2,"3 - Medium","2025-05-07T22:22:49","PS-POT1","Bug",620873,"Services Bug","Implementation"]
[729295,"Calidus\\CTMS","CTMS PSDTTST Polar Speed PDF label has some issues","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polar Speed",2,"3 - Medium","2025-05-07T14:58:29","PS-POT1","Bug",620870,"Functional","Development","CTMS ER047-083"]
[729162,"Calidus\\PORTAL","PORTAL PDSTTST - Order amendment didn't create order items",null,"Closed","Installed on UAT","Polar Speed",2,"3 - Medium","2025-05-07T10:12:34","PS-POT1","Bug",620914,"Functional","Program error (rework)","11.01.020"]
[728088,"Calidus\\CTMS","Import Set From Location (SCR-10)","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polar Speed",2,"3 - Medium","2025-05-02T16:00:19","PS-POT1","Bug",null,"Functional",null,"CTMS ER047-074"]
[725768,"Calidus\\CTMS","Modifications to Order Import CSV","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polar Speed",2,"3 - Medium","2025-04-25T11:45:45","PS-POT1","Bug",620871,"Functional","Development","CTMS ER047-071"]
[725680,"Calidus\\CTMS","Schedule Rules screen display","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polar Speed",2,"3 - Medium","2025-04-25T09:23:33","PS-POT1","Bug",null,"Functional",null,"CTMS ER047-070"]
[722515,"Calidus\\CTMS","WebService TripOrderXML process to only match locations based on Address 1/Address 2/Postcode.","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polarspeed",2,"3 - Medium","2025-04-16T16:11:44","PS-POT1","Bug",620873,null,null,"CTMS ER047-067"]
[716175,"Calidus\\CTMS","Working Days field is displayed even though the new system parameter is not setup","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polar Speed",2,"3 - Medium","2025-03-28T16:36:40","PS-POT1","Bug",620892,"Functional","Development","C-TMS ER047-050"]
[712376,"Calidus\\CTMS","Include Zone value on the ZONE ORS report","Carl Styles <cstyles@aptean.com>","Closed","Installed on UAT","Polarspeed",2,"3 - Medium","2025-03-21T16:38:59","PS-POT1","Bug",null,"Functional",null,"CTMS ER047-065"]
[712335,"Calidus\\CTMS","SCR-CTMS-669852-71 - Multiple Collection Locations / Items arriving at incorrect depot","Carl Styles <cstyles@aptean.com>","Active",null,"Polarspeed",2,null,"2025-03-21T15:30:51","PS-POT5","User Story"]
[676658,"Calidus\\MCS","PROD-CTMS-669852-101 - Mcs Consolidated Pallet Building","Simon Eland <seland@aptean.com>","Active",null,"Polarspeed",1,"3 - Medium","2025-01-06T16:23:29","PS-POT3","User Story",null,"Functional"]
[664597,"Calidus\\PORTAL","664597 Prod-CTMS-669852-100","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-11-25T13:34:18","PS-POT1","User Story",536689,null,null,"CTMS ER047-036"]
[620920,"Calidus\\PORTAL","SCR-PORTAL-669852-63-Batch download POD reports","Simon Eland <seland@aptean.com>","Resolved",null,"Polar Speed",2,null,"2024-07-18T21:49:57","PS-POT4","User Story",536689]
[620919,"Calidus\\CTMS","SCR-PORTAL-669852-62-Display additional order references","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T21:49:23","PS-POT1","User Story",536689,null,null,"CTMS ER047-025"]
[620918,"Calidus\\PORTAL","SCR-PORTAL-669852-58A-APOD POD Upload","Simon Eland <seland@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T21:48:51","PS-POT3","User Story",536689,null,null,"CTMS ER047-040"]
[620917,"Calidus\\PORTAL","SCR-PORTAL-669852-54-Bespoke Polar Speed Client Reports","Harish Thirupathi <hthirupathi@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T21:48:00","PS-POT4","User Story",536689]
[620916,"Calidus\\PORTAL","SCR-PORTAL-669852-53-Print Polar Speed ZPL Labels from Portal","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T21:47:17","PS-POT1","User Story",536689,null,null,"11.01.013"]
[620915,"Calidus\\CTMS","SCR-CTMS-669852-52-Polar Speed ZPL Label Print","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T21:46:46","PS-POT1","User Story",536689,null,null,"CTMS ER047-036"]
[620914,"Calidus\\PORTAL","SCR-PORTAL-669852-14-Allow update of client orders entered through Portal.","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T21:46:13","PS-POT1","User Story",536689,null,null,"CTMS ER047-031"]
[620913,"Calidus\\PORTAL","620913 SCR-PORTAL-669852-06-Portal Order Entry - extend service level selection and validation by customer/address/zone","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T21:45:37","PS-POT1","User Story",536689,null,null,"CTMS ER047-086"]
[620912,"Calidus\\PORTAL","PROD-PORTAL-669852-96-Bug fixes to item entry in Portal Order Entry","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T21:44:52","PS-POT1","User Story",536689,null,null,"Portal 11.01.012"]
[620908,"Calidus\\MCS","SCR-MCS-669852-69-Despatch Confirmation to move entire order if scanned to new trip","Roger Egdell <regdell@aptean.com>","Active",null,"Polar Speed",1,null,"2024-07-18T21:31:38","PS-POT3","User Story"]
[620907,"Calidus\\MCS","SCR-MCS-669852-28-Add and sort by drop number in despatch.","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T21:31:09","PS-POT3","User Story",536689,null,null,"V"]
[620906,"Calidus\\MCS","SCR-MCS-669852-26-Despatch Confirmation Scan of vehicle compartment.","Simon Eland <seland@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T21:30:36","PS-POT3","User Story",536689]
[620905,"Calidus\\MCS","SCR-MCS-669852-19-Quarantine process changes","Tony Walker <twalker@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T21:30:04","PS-POT3","User Story",536689]
[620904,"Calidus\\MCS","SCR-MCS-669852-17-Scan location after scanning item in Receipt and Damages process.","Simon Eland <seland@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T21:29:23","PS-POT3","User Story",536689]
[620903,"Calidus\\MCS","SCR-MCS-669852-15-Changes to Pallet Building","Simon Eland <seland@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T21:28:48","PS-POT3","User Story",536689,null,null,"CTMS ER047-101"]
[620901,"Calidus\\CTMS","SCR-CTMS-669852-70-Day before messages configurable by client","Harish Thirupathi <hthirupathi@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T21:18:00","PS-POT4","User Story",536689]
[620900,"Calidus\\CTMS","SCR-CTMS-669852-68-Manual Rebook Extract","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T21:17:28","PS-POT4","User Story",536689,null,null,"CTMS ER047-060"]
[620899,"Calidus\\CTMS","SCR-CTMS-669852-67-Maintain Original Delivery Type against an order.","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T21:16:55","PS-POT1","User Story",536689,null,null,"CTMS ER047-023"]
[620898,"Calidus\\CTMS","SCR-CTMS-669852-65-Modify Scheduling Engine","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T21:16:26","PS-POT2","User Story",536689,null,null,"CTMS ER047-066"]
[620897,"Calidus\\CTMS","SCR-CTMS-669852-64-Paragon interface changes","Simon Eland <seland@aptean.com>","Active",null,"Polar Speed",1,null,"2024-07-18T21:15:56","PS-POT2","User Story",536689,null,null,"CTMS ER047-096"]
[620896,"Calidus\\CTMS","SCR-CTMS-669852-61-Location opening windows","Simon Eland <seland@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T21:15:24","PS-POT2","User Story",536689,null,null,"CTMS ER047-112"]
[620894,"Calidus\\CTMS","SCR-CTMS-669852-60-Automatic rebooking","Simon Eland <seland@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T21:14:53","PS-POT4","User Story",536689,null,null,"CTMS ER047-056"]
[620892,"Calidus\\CTMS","SCR-CTMS-669852-5A-Offer service levels by day of the week, customer and postal string (zone)","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T21:13:58","PS-POT1","User Story",536689,null,null,"CTMS ER047-036"]
[620891,"Calidus\\CTMS","SCR-CTMS-669852-58-Signature/Signatory details from FlexiPOD to-and TTM.","Simon Eland <seland@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T21:13:28","PS-POT3; STS TS3RDX","User Story",536689,null,null,"CTMS ER047-040"]
[620890,"Calidus\\CTMS","SCR-CTMS-669852-57-Prompt for and store reason for changing order delivery dates and times.","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T21:12:51","PS-POT1","User Story",536689,null,null,"CTMS ER047-023"]
[620889,"Calidus\\CTMS","SCR-CTMS-669852-56-Search orders by postcode or partial postal strings","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T21:12:14","PS-POT1","User Story",536689,null,null,"CTMS ER047-023"]
[620885,"Calidus\\CTMS","SCR-CTMS-669852-55-Bespoke TIMI tracking export process","Simon Eland <seland@aptean.com>","Active",null,"Polar Speed",1,null,"2024-07-18T21:09:00","PS-POT4","User Story",536689,null,null,"CTMS ER047-105"]
[620884,"Calidus\\CTMS","SCR-CTMS-669852-54A-New Reporting Suite formats for Portal Client Reports.","Harish Thirupathi <hthirupathi@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T21:07:12","PS-POT4","User Story",536689,null,null,"CTMS ER047-122"]
[620883,"Calidus\\CTMS","SCR-CTMS-669852-48-Send email/SMS at a defined time the day before","Harish Thirupathi <hthirupathi@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T21:05:58","PS-POT4","User Story",536689,null,null,"CTMS ER047-024"]
[620882,"Calidus\\CTMS","SCR-CTMS-669852-42-Polar Speed specific Finance Export","Simon Eland <seland@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T21:05:13","PS-POT4","User Story",536689]
[620880,"Calidus\\CTMS","SCR-CTMS-669852-25-Add Quarantine Items export to the configurable Reporting Suite.","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T21:04:05","PS-POT4","User Story",536689,null,null,"CTMS ER047-061"]
[620878,"Calidus\\CTMS","SCR-CTMS-669852-23-Interface quarantine status for items out on delivery","Tony Walker <twalker@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T21:02:42","PS-POT4","User Story",536689,null,null,"CTMS ER047-102"]
[620877,"Calidus\\CTMS","SCR-CTMS-669852-21-Quarantine Admin process","Tony Walker <twalker@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T21:02:11","PS-POT4","User Story",536689,null,null,"CTMS ER047-104"]
[620876,"Calidus\\CTMS","SCR-CTMS-669852-20-Quarantine process changes - Reason Codes","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T21:01:36","PS-POT4","User Story",536689,null,null,"CTMS ER047-049"]
[620875,"Calidus\\CTMS","SCR-CTMS-669852-16-Change FlexiPOD interface for final mile consolidation","Simon Eland <seland@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T21:01:01","PS-POT2","User Story",536689]
[620873,"Calidus\\CTMS","SCR-CTMS-669852-11-Order import processes to only match locations based on Name/Address 1/Postcode.","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T20:59:56","PS-POT1","User Story",536689,null,null,"CTMS ER047-026"]
[620872,"Calidus\\CTMS","SCR-CTMS-669852-10A-Allow Configurable CSV imports to be run automatically.","Manjuladevi Mariappan <mm@aptean.com>","Active",null,"Polar Speed",1,null,"2024-07-18T20:59:01","PS-POT4","User Story",536689]
[620871,"Calidus\\CTMS","SCR-CTMS-669852-10-Modifications to Order Import CSV","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T20:58:25","PS-POT1","User Story",536689,null,null,"CTMS ER047-037"]
[620870,"Calidus\\CTMS","SCR-CTMS-669852-08-Polar Speed PDF Label Format","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T20:57:55","PS-POT1","User Story",536689,null,null,"CTMS ER047-022"]
[620869,"Calidus\\CTMS","SCR-CTMS-669852-02-Owning Depot Assignment by specific postcode/postal string","Carl Styles <cstyles@aptean.com>","Closed",null,"Polar Speed",2,null,"2024-07-18T20:57:24","PS-POT1","User Story",536689,null,null,"CTMS ER047-057"]
[620865,"Calidus\\CTMS","PROD-CTMS-669852-97-Do not send trips to Portal TTM at Tendered status","Simon Eland <seland@aptean.com>","Active",null,"Polar Speed",2,null,"2024-07-18T20:55:30","PS-POT4","User Story",536689,null,null,"CTMS ER047-097"]

{"sheet":"Analysis","index":1,"n_rows":41,"n_cols":13,"rows_kept":41}
["Total Bugs"]
["Row Labels","Count of State","%age"]
["Active",30,{"v":0.35714285714285715,"d":"35.71%"}]
["Closed",48,{"v":0.5714285714285714,"d":"57.14%"}]
["New",5,{"v":0.05952380952380952,"d":"5.95%"}]
["Resolved",1,{"v":0.011904761904761904,"d":"1.19%"}]
["(blank)",null,{"v":0,"d":"0.00%"}]
["Grand Total",84,{"v":1,"d":"100.00%"}]
[]
[]
["Bugs by Severity",{"$nulls":4},"Bugs by Priority",{"$nulls":4},"Bugs by System"]
["State","(All)",{"$nulls":3},"State","(All)",{"$nulls":3},"State","(All)"]
[]
["Row Labels","Count of Severity","%age",null,null,"Row Labels","Count of Priority","%age",null,null,"Row Labels","Count of Area Path","%age"]
["1 - Critical",2,{"v":0.05263157894736842,"d":"5.26%"},null,null,1,10,{"v":0.06289308176100629,"d":"6.29%"},null,null,"Calidus\\CTMS",59,{"v":0.7023809523809523,"d":"70.24%"}]
["2 - High",1,{"v":0.02631578947368421,"d":"2.63%"},null,null,2,73,{"v":0.9182389937106918,"d":"91.82%"},null,null,"Calidus\\MCS",14,{"v":0.16666666666666666,"d":"16.67%"}]
["3 - Medium",35,{"v":0.9210526315789473,"d":"92.11%"},null,null,3,1,{"v":0.018867924528301886,"d":"1.89%"},null,null,"Calidus\\PORTAL",11,{"v":0.13095238095238096,"d":"13.10%"}]
["(blank)",null,{"v":0,"d":"0.00%"},null,null,"(blank)",null,{"v":0,"d":"0.00%"},null,null,"(blank)",null,{"v":0,"d":"0.00%"}]
["Grand Total",38,{"v":1,"d":"100.00%"},null,null,"Grand Total",84,{"v":1,"d":"100.00%"},null,null,"Grand Total",84,{"v":1,"d":"100.00%"}]
[]
[]
["Bugs by Bug Type",{"$nulls":4},"Bugs by Fault",{"$nulls":4},"Bugs by Parent"]
["Row Labels","Count of Bug Type","%age",null,null,"Row Labels","Count of Fault","%age",null,null,"Row Labels","Count of Parent","Count of Parent2"]
["Functional",29,{"v":0.8529411764705882,"d":"85.29%"},null,null,"Design constraint",1,{"v":0.03333333333333333,"d":"3.33%"},null,null,536689,41,{"v":0.6721311475409836,"d":"67.21%"}]
["Design error",1,{"v":0.029411764705882353,"d":"2.94%"},null,null,"Design error",1,{"v":0.03333333333333333,"d":"3.33%"},null,null,620870,1,{"v":0.01639344262295082,"d":"1.64%"}]
["Development",4,{"v":0.11764705882352941,"d":"11.76%"},null,null,"Development",4,{"v":0.13333333333333333,"d":"13.33%"},null,null,620871,2,{"v":0.03278688524590164,"d":"3.28%"}]
["Missing function",2,{"v":0.058823529411764705,"d":"5.88%"},null,null,"Implementation",2,{"v":0.06666666666666667,"d":"6.67%"},null,null,620873,2,{"v":0.03278688524590164,"d":"3.28%"}]
["Program error (rework)",14,{"v":0.4117647058823529,"d":"41.18%"},null,null,"Missing function",2,{"v":0.06666666666666667,"d":"6.67%"},null,null,620876,1,{"v":0.01639344262295082,"d":"1.64%"}]
["User error",1,{"v":0.029411764705882353,"d":"2.94%"},null,null,"Program error",1,{"v":0.03333333333333333,"d":"3.33%"},null,null,620877,3,{"v":0.04918032786885246,"d":"4.92%"}]
["Version/release control",1,{"v":0.029411764705882353,"d":"2.94%"},null,null,"Program error (rework)",14,{"v":0.4666666666666667,"d":"46.67%"},null,null,620892,1,{"v":0.01639344262295082,"d":"1.64%"}]
["(blank)",6,{"v":0.17647058823529413,"d":"17.65%"},null,null,"User error",4,{"v":0.13333333333333333,"d":"13.33%"},null,null,620894,3,{"v":0.04918032786885246,"d":"4.92%"}]
["Services Bug",2,{"v":0.058823529411764705,"d":"5.88%"},null,null,"Version/release control",1,{"v":0.03333333333333333,"d":"3.33%"},null,null,620896,1,{"v":0.01639344262295082,"d":"1.64%"}]
["Implementation",1,{"v":0.029411764705882353,"d":"2.94%"},null,null,"(blank)",null,{"v":0,"d":"0.00%"},null,null,620897,1,{"v":0.01639344262295082,"d":"1.64%"}]
["Program error",1,{"v":0.029411764705882353,"d":"2.94%"},null,null,"Grand Total",30,{"v":1,"d":"100.00%"},null,null,620903,1,{"v":0.01639344262295082,"d":"1.64%"}]
["Setup",3,{"v":0.08823529411764706,"d":"8.82%"},{"$nulls":7},620904,1,{"v":0.01639344262295082,"d":"1.64%"}]
["User error",3,{"v":0.08823529411764706,"d":"8.82%"},{"$nulls":7},620906,1,{"v":0.01639344262295082,"d":"1.64%"}]
["(blank)",null,{"v":0,"d":"0.00%"},{"$nulls":7},620907,1,{"v":0.01639344262295082,"d":"1.64%"}]
["Design constraint",null,{"v":0,"d":"0.00%"},{"$nulls":7},620914,1,{"v":0.01639344262295082,"d":"1.64%"}]
["Implementation",null,{"v":0,"d":"0.00%"},{"$nulls":7},"(blank)",null,{"v":0,"d":"0.00%"}]
["(blank)",null,{"v":0,"d":"0.00%"},{"$nulls":7},"Grand Total",61,{"v":1,"d":"100.00%"}]
["Grand Total",34,{"v":1,"d":"100.00%"}]